## Sheet1
Project_ID | Project_Name | Project_Type | Region | Operator | Subcontractor | Status | Budgeted_Cost | Actual_Cost | Phase_Planning | Phase_Drilling_Construction | Phase_Completion | Phase_Closeout | Planned_Start | Planned_End | Actual_End | Schedule_Variance_Days | Change_Order_Count | Change_Order_Cost | Cost_Variance | Cost_Variance_Pct | Change_Order_Budget_Impact_Pct | On_Time
OG-1000 | Permian Basin Well Drilling 1 | Well Drilling | Permian Basin | Kirby Inc Energy | Myers and Sons Services | Completed | 4050931.88 | 4555301.75 | 2334910.66 | 1618869.39 | 300786.19 | 300735.51 | 2024-01-31 | 2024-06-10 | 2024-06-15 | 5 | 1 | 68531.59 | 504369.87 | 12.45 | 1.69 | No
OG-1001 | Permian Basin Maitenance Turnaround 2 | Maitenance Turnaround | Permian Basin | Tucker-Miller Energy | Smith-Patrick Services | Active | 1858580.98 | 2391774.26 | 8964.32 | 1510002.33 | 769935.36 | 102872.26 | 2023-06-17 | 2023-12-13 | 2024-01-15 | 33 | 8 | 223780.11 | 533193.28 | 28.69 | 12.04 | No
OG-1002 | Eagle Ford Maitenance Turnaround 3 | Maitenance Turnaround | Eagle Ford | Watson Inc Energy | Rodriguez-Williams Services | Delayed | 9044352.42 | 8867873.1 | 1595312.26 | 3271633.32 | 2487109.42 | 1513818.1 | 2024-04-14 | 2024-06-16 | 2024-06-13 | -3 | 2 | 315710.94 | -176479.32 | -1.95 | 3.49 | Yes
OG-1003 | Eagle Ford Pipeline Construction 4 | Pipeline Construction | Eagle Ford | Jones and Sons Energy | Hart, Perry and Stevens Services | Delayed | 1982049.01 | 1780029.32 | 208578.48 | 275442.36 | 367597.6 | 928410.87 | 2025-03-01 | 2025-11-10 | 2025-11-29 | 19 | 1 | 17787.87 | -202019.69 | -10.19 | 0.9 | No
OG-1004 | Permian Basin Facility Upgrade 5 | Facility Upgrade | Permian Basin | Watson Inc Energy | Myers and Sons Services | Delayed | 8275307.33 | 8772895.19 | 3808579.07 | 201838.14 | 3969104.21 | 793373.78 | 2025-11-07 | 2026-07-18 | 2026-06-16 | -32 | 1 | 114207.65 | 497587.86 | 6.01 | 1.38 | Yes
OG-1005 | Permian Basin Pipeline Construction 6 | Pipeline Construction | Permian Basin | Tucker-Miller Energy | Smith Inc Services | Completed | 10088318.12 | 9683818.9 | 4383604.79 | 2205931.31 | 494934.36 | 2599348.45 | 2024-11-12 | 2025-06-08 | 2025-06-09 | 1 | 1 | 215717.93 | -404499.22 | -4.01 | 2.14 | No
OG-1006 | Midland Facility Upgrade 7 | Facility Upgrade | Midland | Jones and Sons Energy | Hart, Perry and Stevens Services | Completed | 2858484.41 | 3354093.4 | 595696.32 | 1170689.76 | 1261767.95 | 325939.37 | 2023-12-31 | 2024-08-28 | 2024-08-02 | -26 | 3 | 143676.4 | 495608.99 | 17.34 | 5.03 | Yes
OG-1007 | Eagle Ford Pipeline Construction 8 | Pipeline Construction | Eagle Ford | Jimenez and Sons Energy | Wilson LLC Services | Delayed | 7202773.07 | 8360762.8 | 1032062.31 | 2429739.17 | 515521.41 | 4383439.91 | 2025-11-22 | 2026-06-08 | 2026-06-23 | 15 | 8 | 316367.65 | 1157989.73 | 16.08 | 4.39 | No
OG-1008 | Permian Basin Pipeline Construction 9 | Pipeline Construction | Permian Basin | Jones and Sons Energy | Oconnell, Santos and Richardson Services | Delayed | 6316889.41 | 5231784.89 | 2782339.26 | 695722.84 | 520030.21 | 1233692.58 | 2024-11-07 | 2025-02-08 | 2025-01-28 | -11 | 3 | 432613.49 | -1085104.52 | -17.18 | 6.85 | Yes
OG-1009 | Midland Maitenance Turnaround 10 | Maitenance Turnaround | Midland | Watson Inc Energy | Myers and Sons Services | Delayed | 2571638.06 | 2825233.96 | 35808.96 | 2003220.63 | 683809.96 | 102394.41 | 2024-06-27 | 2024-11-05 | 2024-11-04 | -1 | 3 | 143688.15 | 253595.9 | 9.86 | 5.59 | Yes
OG-1010 | Midland Maitenance Turnaround 11 | Maitenance Turnaround | Midland | Jones and Sons Energy | Bender PLC Services | Completed | 3680151.01 | 4433293.65 | 3086117.71 | 160934.4 | 928614.12 | 257627.42 | 2024-01-10 | 2024-05-19 | 2024-06-25 | 37 | 8 | 363242.56 | 753142.64 | 20.46 | 9.87 | No
OG-1011 | Eagle Ford Pipeline Construction 12 | Pipeline Construction | Eagle Ford | Collins, Nolan and Edwards Energy | Sawyer Ltd Services | Over Budeget | 9147930.95 | 10059883.75 | 3277617.02 | 535651.32 | 3038369.92 | 3208245.5 | 2025-07-19 | 2026-04-02 | 2026-05-11 | 39 | 6 | 817671.93 | 911952.8 | 9.97 | 8.94 | No
OG-1012 | Permian Basin Facility Upgrade 13 | Facility Upgrade | Permian Basin | Rodriguez, Castro and Ryan Energy | Bender PLC Services | Delayed | 10384800.35 | 12169728.13 | 6326482.04 | 1852691.89 | 369260.38 | 3621293.83 | 2024-04-02 | 2025-03-02 | 2025-04-21 | 50 | 4 | 798174.44 | 1784927.78 | 17.19 | 7.69 | No
OG-1013 | Midland Facility Upgrade 14 | Facility Upgrade | Midland | Jimenez and Sons Energy | Lee, Howard and Ortega Services | Completed | 7078993.74 | 7816691.01 | 3337277.69 | 1541545.07 | 1674829.02 | 1263039.24 | 2026-01-26 | 2026-08-08 | 2026-10-03 | 56 | 8 | 1078785.13 | 737697.27 | 10.42 | 15.24 | No
OG-1014 | Eagle Ford Pipeline Construction 15 | Pipeline Construction | Eagle Ford | Jones and Sons Energy | Sims-Kramer Services | Delayed | 11556406.6 | 12285119.63 | 1234441.8 | 2323797.02 | 7788975.47 | 937905.34 | 2024-11-16 | 2025-10-18 | 2025-10-19 | 1 | 8 | 2122896.86 | 728713.03 | 6.31 | 18.37 | No
OG-1015 | Permian Basin Well Drilling 16 | Well Drilling | Permian Basin | Jones and Sons Energy | Ortiz-Maxwell Services | Completed | 13241467.23 | 16838963.43 | 5099735.66 | 1572373.12 | 6715898.68 | 3450955.96 | 2024-08-05 | 2025-03-10 | 2025-03-05 | -5 | 3 | 57526.06 | 3597496.2 | 27.17 | 0.43 | Yes
OG-1016 | Permian Basin Maitenance Turnaround 17 | Maitenance Turnaround | Permian Basin | Page-Jordan Energy | Rodriguez-Williams Services | Active | 11604599.22 | 13778260.39 | 4634055.7 | 587794.71 | 6350068.06 | 2206341.92 | 2024-09-21 | 2025-01-24 | 2025-02-12 | 19 | 7 | 1922864.9 | 2173661.17 | 18.73 | 16.57 | No
OG-1017 | Eagle Ford Maitenance Turnaround 18 | Maitenance Turnaround | Eagle Ford | Page-Jordan Energy | Miranda LLC Services | Delayed | 11451345.35 | 10817994.75 | 623140.11 | 1341873.9 | 4104287 | 4748693.73 | 2025-04-23 | 2025-10-02 | 2025-10-02 | 0 | 4 | 456899.86 | -633350.6 | -5.53 | 3.99 | Yes
OG-1018 | Permian Basin Maitenance Turnaround 19 | Maitenance Turnaround | Permian Basin | Nelson, Snyder and Jackson Energy | Myers and Sons Services | Active | 3758111.39 | 3948899.5 | 1602883.21 | 745163.41 | 378802.26 | 1222050.62 | 2026-01-30 | 2026-09-20 | 2026-09-22 | 2 | 0 | 0 | 190788.11 | 5.08 | 0 | No
OG-1019 | Permian Basin Pipeline Construction 20 | Pipeline Construction | Permian Basin | Rodriguez, Castro and Ryan Energy | Powers Ltd Services | Completed | 10763693.72 | 11041473.91 | 1353879.98 | 2247209.99 | 836580.6 | 6603803.34 | 2024-02-10 | 2024-05-10 | 2024-06-01 | 22 | 3 | 54410.74 | 277780.19 | 2.58 | 0.51 | No
OG-1020 | Eagle Ford Well Drilling 21 | Well Drilling | Eagle Ford | Kirby Inc Energy | Ford, Rivera and Mcdonald Services | Over Budeget | 10200177.79 | 7774415.55 | 1295511.92 | 145238.44 | 3634362.02 | 2699303.17 | 2024-07-06 | 2024-12-22 | 2024-12-31 | 9 | 8 | 269920.88 | -2425762.24 | -23.78 | 2.65 | No
OG-1021 | Midland Maitenance Turnaround 22 | Maitenance Turnaround | Midland | Nelson, Snyder and Jackson Energy | Wilson LLC Services | Over Budeget | 1867724.05 | 1907218.67 | 55801.76 | 239658.61 | 1512958.81 | 98799.49 | 2024-11-17 | 2025-08-24 | 2025-09-12 | 19 | 5 | 98891 | 39494.62 | 2.11 | 5.29 | No
OG-1022 | Permian Basin Well Drilling 23 | Well Drilling | Permian Basin | Collins, Nolan and Edwards Energy | Hunt-Clark Services | Over Budeget | 11059097.03 | 13507840.14 | 1208372.51 | 5801745.44 | 2042014.77 | 4455707.41 | 2026-01-19 | 2026-05-14 | 2026-06-15 | 32 | 3 | 158910.99 | 2448743.11 | 22.14 | 1.44 | No
OG-1023 | Eagle Ford Maitenance Turnaround 24 | Maitenance Turnaround | Eagle Ford | Kirby Inc Energy | Wilson LLC Services | Completed | 7208106.99 | 8203031.65 | 311555.65 | 5938293.49 | 1273528.5 | 679654.02 | 2023-08-17 | 2023-11-23 | 2024-02-06 | 75 | 7 | 1019254.39 | 994924.66 | 13.8 | 14.14 | No
OG-1024 | Permian Basin Well Drilling 25 | Well Drilling | Permian Basin | Nelson, Snyder and Jackson Energy | Wilson LLC Services | Over Budeget | 2911511.1 | 3100607.06 | 1653025.08 | 24429.05 | 1048071.33 | 375081.6 | 2025-11-27 | 2026-10-01 | 2026-09-26 | -5 | 7 | 108907.34 | 189095.96 | 6.49 | 3.74 | Yes
OG-1025 | Midland Pipeline Construction 26 | Pipeline Construction | Midland | Tucker-Miller Energy | Hunt-Clark Services | Over Budeget | 14786978.23 | 13170087.86 | 3382832.61 | 1408659.34 | 7952377.34 | 426218.57 | 2025-03-13 | 2025-09-24 | 2025-10-18 | 24 | 7 | 738145.47 | -1616890.37 | -10.93 | 4.99 | No
OG-1026 | Gulf Coast Pipeline Construction 27 | Pipeline Construction | Gulf Coast | Nelson, Snyder and Jackson Energy | Wilson LLC Services | Delayed | 14546285.79 | 13564586.14 | 5787336.7 | 4695618.58 | 667592.36 | 2414038.5 | 2024-12-05 | 2025-11-26 | 2025-11-26 | 0 | 8 | 177341.25 | -981699.65 | -6.75 | 1.22 | Yes
OG-1027 | Midland Well Drilling 28 | Well Drilling | Midland | Page-Jordan Energy | Moore-Moses Services | Completed | 13831113.4 | 14994572.69 | 3322584.64 | 1219637.45 | 430481.55 | 10021869.05 | 2025-08-28 | 2026-07-25 | 2026-09-12 | 49 | 2 | 39335.4 | 1163459.29 | 8.41 | 0.28 | No
OG-1028 | Permian Basin Well Drilling 29 | Well Drilling | Permian Basin | Nelson, Snyder and Jackson Energy | Hart, Perry and Stevens Services | Completed | 6354745.49 | 6920206.12 | 649404.42 | 673748.24 | 2030282.96 | 3566770.49 | 2023-04-30 | 2024-04-15 | 2024-05-18 | 33 | 3 | 275916.25 | 565460.63 | 8.9 | 4.34 | No
OG-1029 | Midland Well Drilling 30 | Well Drilling | Midland | Stevens, Parsons and Thomas Energy | Ford, Rivera and Mcdonald Services | Delayed | 8695790.4 | 9457314.92 | 2714061.82 | 232201.98 | 465753.35 | 6045297.77 | 2024-09-28 | 2025-05-07 | 2025-05-27 | 20 | 4 | 177619.52 | 761524.52 | 8.76 | 2.04 | No
OG-1030 | Midland Facility Upgrade 31 | Facility Upgrade | Midland | Jimenez and Sons Energy | Coleman, Wall and Jordan Services | Completed | 10239508.23 | 11201621.34 | 26396.32 | 911961.69 | 4139078.65 | 6124184.69 | 2026-01-17 | 2026-08-18 | 2026-08-07 | -11 | 7 | 566562.33 | 962113.11 | 9.4 | 5.53 | Yes
OG-1031 | Permian Basin Maitenance Turnaround 32 | Maitenance Turnaround | Permian Basin | Rodriguez, Castro and Ryan Energy | Ortiz-Maxwell Services | Delayed | 8295698.86 | 7228079.54 | 2742637.05 | 596403.54 | 866856.19 | 3022182.77 | 2024-01-02 | 2024-11-16 | 2024-12-15 | 29 | 4 | 109881.98 | -1067619.32 | -12.87 | 1.32 | No
OG-1032 | Gulf Coast Pipeline Construction 33 | Pipeline Construction | Gulf Coast | Kirby Inc Energy | Smith-Patrick Services | Completed | 2787329.07 | 3329482.47 | 1445571.9 | 1132981.33 | 132655.76 | 618273.48 | 2024-11-11 | 2025-10-15 | 2025-11-06 | 22 | 4 | 170494.72 | 542153.4 | 19.45 | 6.12 | No
OG-1033 | Permian Basin Facility Upgrade 34 | Facility Upgrade | Permian Basin | Jimenez and Sons Energy | Hart, Perry and Stevens Services | Delayed | 4334755.86 | 3973119.47 | 1956641.8 | 270497.99 | 1205764.01 | 540215.67 | 2023-07-07 | 2023-10-29 | 2023-10-15 | -14 | 8 | 134765.75 | -361636.39 | -8.34 | 3.11 | Yes
OG-1034 | Gulf Coast Pipeline Construction 35 | Pipeline Construction | Gulf Coast | Nelson, Snyder and Jackson Energy | Ortiz-Maxwell Services | Completed | 10468708.37 | 11012560.74 | 3118600.75 | 2459236.06 | 787539.25 | 4647184.67 | 2025-06-13 | 2025-12-25 | 2026-02-16 | 53 | 8 | 1022859.5 | 543852.37 | 5.2 | 9.77 | No
OG-1035 | Gulf Coast Maitenance Turnaround 36 | Maitenance Turnaround | Gulf Coast | Tucker-Miller Energy | Smith-Patrick Services | Over Budeget | 551412.49 | 490407.59 | 156778.24 | 171031.76 | 136906.54 | 25691.06 | 2023-12-19 | 2024-04-23 | 2024-05-17 | 24 | 4 | 8909.83 | -61004.9 | -11.06 | 1.62 | No
OG-1036 | Permian Basin Maitenance Turnaround 37 | Maitenance Turnaround | Permian Basin | Rodriguez, Castro and Ryan Energy | Myers and Sons Services | Delayed | 1591035.97 | 1783528.48 | 974275.64 | 563733.43 | 102544.1 | 142975.32 | 2024-12-04 | 2025-04-19 | 2025-04-26 | 7 | 8 | 11464.41 | 192492.51 | 12.1 | 0.72 | No
OG-1037 | Midland Pipeline Construction 38 | Pipeline Construction | Midland | Jimenez and Sons Energy | Ford, Rivera and Mcdonald Services | Active | 1106518.44 | 1087732.81 | 40880.13 | 179118.7 | 605611.04 | 262122.94 | 2025-08-30 | 2026-05-03 | 2026-06-07 | 35 | 0 | 0 | -18785.63 | -1.7 | 0 | No
OG-1038 | Gulf Coast Well Drilling 39 | Well Drilling | Gulf Coast | Page-Jordan Energy | Moore-Moses Services | Active | 13319953.17 | 12220009.88 | 1809407.45 | 8739791.32 | 286084.91 | 1384726.19 | 2023-10-30 | 2024-07-24 | 2024-08-07 | 14 | 2 | 616556.54 | -1099943.29 | -8.26 | 4.63 | No
OG-1039 | Midland Pipeline Construction 40 | Pipeline Construction | Midland | Tucker-Miller Energy | Rodriguez-Williams Services | Active | 3100729.62 | 3422176.38 | 1277212.08 | 1296693.31 | 476509.83 | 371761.16 | 2025-07-18 | 2026-03-05 | 2026-03-31 | 26 | 6 | 373127.14 | 321446.76 | 10.37 | 12.03 | No
OG-1040 | Permian Basin Pipeline Construction 41 | Pipeline Construction | Permian Basin | Collins, Nolan and Edwards Energy | Mendoza Inc Services | Over Budeget | 13146418.35 | 14819369.63 | 5090305.3 | 6166575.63 | 1806354.53 | 1756134.17 | 2023-05-25 | 2024-03-20 | 2024-04-14 | 25 | 3 | 196775.09 | 1672951.28 | 12.73 | 1.5 | No
OG-1041 | Eagle Ford Facility Upgrade 42 | Facility Upgrade | Eagle Ford | Nelson, Snyder and Jackson Energy | Rodriguez-Williams Services | Completed | 843134.3 | 957491.62 | 213895.04 | 280696.91 | 390017.18 | 72882.49 | 2024-09-02 | 2025-02-07 | 2025-03-23 | 44 | 6 | 41515.34 | 114357.32 | 13.56 | 4.92 | No
OG-1042 | Midland Facility Upgrade 43 | Facility Upgrade | Midland | Page-Jordan Energy | Moore-Moses Services | Delayed | 5301673.09 | 4952166.75 | 1851848.85 | 78508.42 | 1343945.46 | 1677864.02 | 2024-03-14 | 2024-05-27 | 2024-05-29 | 2 | 1 | 116244.27 | -349506.34 | -6.59 | 2.19 | No
OG-1043 | Permian Basin Facility Upgrade 44 | Facility Upgrade | Permian Basin | Rodriguez, Castro and Ryan Energy | Smith Inc Services | Completed | 9150283.2 | 10549718.62 | 145559.84 | 178870.24 | 8126669.88 | 2098618.67 | 2024-03-22 | 2024-11-13 | 2024-10-06 | -38 | 5 | 499140.95 | 1399435.42 | 15.29 | 5.45 | Yes
OG-1044 | Gulf Coast Pipeline Construction 45 | Pipeline Construction | Gulf Coast | Tucker-Miller Energy | Mendoza Inc Services | Active | 10777386.62 | 11420171.54 | 6043371.81 | 999730.92 | 4010222.17 | 366846.65 | 2024-12-25 | 2025-02-23 | 2025-02-01 | -22 | 8 | 1995056.28 | 642784.92 | 5.96 | 18.51 | Yes
OG-1045 | Permian Basin Maitenance Turnaround 46 | Maitenance Turnaround | Permian Basin | Jones and Sons Energy | Powers Ltd Services | Over Budeget | 9535753.44 | 10077725.39 | 1151021.52 | 1501142.51 | 1916065.65 | 5509495.71 | 2024-03-11 | 2024-07-12 | 2024-07-03 | -9 | 4 | 483579.52 | 541971.95 | 5.68 | 5.07 | Yes
OG-1046 | Gulf Coast Maitenance Turnaround 47 | Maitenance Turnaround | Gulf Coast | Page-Jordan Energy | Hart, Perry and Stevens Services | Active | 2345673.09 | 1750408.37 | 1083690.63 | 215863.79 | 395013.82 | 55840.13 | 2025-01-30 | 2025-11-01 | 2025-11-16 | 15 | 6 | 238314.97 | -595264.72 | -25.38 | 10.16 | No
OG-1047 | Midland Facility Upgrade 48 | Facility Upgrade | Midland | Page-Jordan Energy | Miranda LLC Services | Delayed | 12589014.95 | 14172059.56 | 6346384.39 | 2296731.54 | 2053117.46 | 3475826.17 | 2024-11-11 | 2025-06-14 | 2025-07-19 | 35 | 4 | 264599.3 | 1583044.61 | 12.57 | 2.1 | No
OG-1048 | Midland Maitenance Turnaround 49 | Maitenance Turnaround | Midland | Nelson, Snyder and Jackson Energy | Ortiz-Maxwell Services | Delayed | 7912022.95 | 10402871.27 | 1921113.05 | 584512.44 | 5514045.1 | 2383200.68 | 2024-04-27 | 2024-09-20 | 2024-10-12 | 22 | 1 | 56133.11 | 2490848.32 | 31.48 | 0.71 | No
OG-1049 | Gulf Coast Pipeline Construction 50 | Pipeline Construction | Gulf Coast | Nelson, Snyder and Jackson Energy | Hart, Perry and Stevens Services | Over Budeget | 12195161.97 | 16686925.85 | 3378739.8 | 1767885.1 | 2732701.79 | 8807599.16 | 2023-05-31 | 2023-10-13 | 2023-11-22 | 40 | 0 | 0 | 4491763.88 | 36.83 | 0 | No