## Data
Project_ID | Project_Name | Project_Type | Region | Operator | Subcontractor | Status | Budgeted_Cost | Actual_Cost | Phase_Planning | Phase_Drilling_Construction | Phase_Completion | Phase_Closeout | Planned_Start | Planned_End | Actual_End | Schedule_Variance_Days | Change_Order_Count | Change_Order_Cost | Cost_Variance | Cost_Variance_Pct | Change_Order_Budget_Impact_Pct | On_Time | Risk_Flag | Budget_Health | Change_Order_Risk
OG-1000 | Midland Maintenance Turnaround 1 | Maintenance Turnaround | Midland | Freeman, Barnes and Gonzalez Energy | Powell and Sons Services | Completed | 9191866.96 | 9983647.76 | 1631312.81 | 4253314.74 | 77843.57 | 4021176.63 | 2025-09-14 | 2026-03-10 | 2026-03-15 | 5 | 3 | 82671.62 | 791780.8 | 8.61 | 0.9 | No | High Risk | Watch | Moderate CO Impact
OG-1001 | Permian Basin Maintenance Turnaround 2 | Maintenance Turnaround | Permian Basin | Silva PLC Energy | Ellis-Wheeler Services | Delayed | 7594486.89 | 6826010.25 | 52705.62 | 5146957.7 | 7548.71 | 1618798.22 | 2024-07-07 | 2025-04-08 | 2025-04-30 | 22 | 3 | 406316.03 | -768476.64 | -10.12 | 5.35 | No | Medium Risk | Under Budget | No Change Orders
OG-1002 | Eagle Ford Pipeline Construction 3 | Pipeline Construction | Eagle Ford | Williams and Sons Energy | Cannon LLC Services | Completed | 10078234.49 | 9460634.92 | 862300.13 | 3345838.09 | 636786.39 | 4615710.3 | 2026-03-05 | 2027-02-18 | 2027-02-20 | 2 | 5 | 94066.41 | -617599.57 | -6.13 | 0.93 | No | Medium Risk | On Track | No Change Orders
OG-1003 | Midland Facility Upgrade 4 | Facility Upgrade | Midland | Moreno, Walker and Robinson Energy | Grimes LLC Services | Completed | 4406288.62 | 3510959.62 | 1919321.87 | 272019.44 | 924281.32 | 395336.99 | 2025-09-15 | 2025-11-17 | 2025-12-15 | 28 | 6 | 121209.05 | -895329 | -20.32 | 2.75 | No | Medium Risk | Under Budget | No Change Orders
OG-1004 | Midland Pipeline Construction 5 | Pipeline Construction | Midland | Moreno, Walker and Robinson Energy | Nelson, Miller and Johnson Services | Over Budget | 5684111.41 | 6616426.66 | 864928.92 | 3574456.57 | 345373.41 | 1831667.76 | 2023-11-05 | 2024-04-23 | 2024-03-18 | -36 | 2 | 191201.42 | 932315.25 | 16.4 | 3.36 | Yes | Medium Risk | Critical | High CO Impact
OG-1005 | Eagle Ford Pipeline Construction 6 | Pipeline Construction | Eagle Ford | Moreno, Walker and Robinson Energy | Miller Inc Services | Over Budget | 2091990.07 | 1719627.34 | 332165.61 | 901791.09 | 112517.4 | 373153.24 | 2023-06-11 | 2023-11-05 | 2023-09-22 | -44 | 7 | 225325.51 | -372362.73 | -17.8 | 10.77 | Yes | Clean | Under Budget | No Change Orders
OG-1006 | Permian Basin Maintenance Turnaround 7 | Maintenance Turnaround | Permian Basin | Hale, Garrett and Lee Energy | Pierce-Mendoza Services | Over Budget | 4992200.42 | 5987256.26 | 1090533.6 | 248890.56 | 3587711.66 | 1060120.44 | 2024-06-10 | 2024-08-11 | 2024-07-01 | -41 | 6 | 222198.78 | 995055.84 | 19.93 | 4.45 | Yes | Medium Risk | Critical | High CO Impact
OG-1007 | Eagle Ford Well Drilling 8 | Well Drilling | Eagle Ford | Williams and Sons Energy | Jones Ltd Services | Over Budget | 4234860.32 | 4287535.29 | 926970.18 | 1462707.75 | 1633748.48 | 264108.88 | 2023-12-19 | 2024-09-10 | 2024-10-22 | 42 | 2 | 67424.84 | 52674.97 | 1.24 | 1.59 | No | Medium Risk | On Track | Low CO Impact
OG-1008 | Eagle Ford Pipeline Construction 9 | Pipeline Construction | Eagle Ford | Silva PLC Energy | Jacobs, Hood and Taylor Services | Delayed | 14147739.42 | 13908912.38 | 2362526.83 | 6141335.92 | 3649887.55 | 1755162.08 | 2025-09-20 | 2026-01-21 | 2026-02-27 | 37 | 1 | 37789.78 | -238827.04 | -1.69 | 0.27 | No | Medium Risk | On Track | No Change Orders
OG-1009 | Midland Pipeline Construction 10 | Pipeline Construction | Midland | Hale, Garrett and Lee Energy | Powell and Sons Services | Active | 13899941.42 | 16952211.65 | 5550694.48 | 1732148.71 | 3846544.54 | 5822823.92 | 2023-09-04 | 2024-08-16 | 2024-07-10 | -37 | 5 | 1204969.31 | 3052270.23 | 21.96 | 8.67 | Yes | Medium Risk | Critical | High CO Impact
OG-1010 | Gulf Coast Well Drilling 11 | Well Drilling | Gulf Coast | Hale, Garrett and Lee Energy | Harris, Lynn and Aguilar Services | Completed | 10335707.5 | 9870386.38 | 1444937.17 | 5279237.89 | 1720589.89 | 1425621.43 | 2024-12-29 | 2025-11-10 | 2025-10-15 | -26 | 4 | 10370.48 | -465321.12 | -4.5 | 0.1 | Yes | Clean | On Track | No Change Orders
OG-1011 | Midland Pipeline Construction 12 | Pipeline Construction | Midland | Callahan-Morris Energy | Bautista-Caldwell Services | Delayed | 5382932.68 | 4825974.4 | 169178.67 | 351532.3 | 1229937.82 | 3075325.61 | 2023-03-21 | 2023-12-10 | 2023-10-28 | -43 | 6 | 300899.5 | -556958.28 | -10.35 | 5.59 | Yes | Clean | Under Budget | No Change Orders
OG-1012 | Eagle Ford Well Drilling 13 | Well Drilling | Eagle Ford | Moreno, Walker and Robinson Energy | Williams, Beard and Madden Services | Active | 13884024.33 | 12583052.78 | 124634.78 | 5163421.15 | 2941016.22 | 4353980.62 | 2025-07-31 | 2026-04-21 | 2026-05-28 | 37 | 7 | 503407.56 | -1300971.55 | -9.37 | 3.63 | No | Medium Risk | On Track | No Change Orders
OG-1013 | Gulf Coast Well Drilling 14 | Well Drilling | Gulf Coast | Freeman, Barnes and Gonzalez Energy | Grimes LLC Services | Completed | 11577902.51 | 9569822.15 | 1773638.22 | 2207507.15 | 2028568.7 | 3560108.09 | 2023-12-28 | 2024-07-02 | 2024-07-31 | 29 | 6 | 463241.83 | -2008080.36 | -17.34 | 4 | No | Medium Risk | Under Budget | No Change Orders
OG-1014 | Gulf Coast Maintenance Turnaround 15 | Maintenance Turnaround | Gulf Coast | Smith LLC Energy | Garcia, Wright and Graham Services | Delayed | 7795684.56 | 6763795.28 | 243625.7 | 2078591.93 | 609985.2 | 3831592.44 | 2023-06-08 | 2024-01-18 | 2024-01-15 | -3 | 7 | 654727.97 | -1031889.28 | -13.24 | 8.4 | Yes | Clean | Under Budget | No Change Orders
OG-1015 | Midland Facility Upgrade 16 | Facility Upgrade | Midland | Silva PLC Energy | Pierce-Mendoza Services | Delayed | 2811587.42 | 3080136.02 | 1248954.72 | 311296.77 | 1012034.35 | 507850.17 | 2026-01-03 | 2026-09-14 | 2026-08-21 | -24 | 7 | 86117.03 | 268548.6 | 9.55 | 3.06 | Yes | Medium Risk | Watch | Moderate CO Impact
OG-1016 | Permian Basin Facility Upgrade 17 | Facility Upgrade | Permian Basin | Munoz PLC Energy | Garcia, Wright and Graham Services | Delayed | 10567893.6 | 10802592.85 | 1096716.65 | 3415259.52 | 2613340.86 | 3677275.82 | 2025-12-25 | 2026-06-01 | 2026-06-27 | 26 | 2 | 375447.29 | 234699.25 | 2.22 | 3.55 | No | Medium Risk | On Track | Low CO Impact
OG-1017 | Midland Pipeline Construction 18 | Pipeline Construction | Midland | Munoz PLC Energy | Mendoza-Wagner Services | Active | 10020066.73 | 10153265.18 | 475781.56 | 8635016.9 | 181160.33 | 861306.4 | 2025-11-19 | 2026-01-19 | 2025-12-19 | -31 | 1 | 113099.15 | 133198.45 | 1.33 | 1.13 | Yes | Clean | On Track | Low CO Impact
OG-1018 | Eagle Ford Facility Upgrade 19 | Facility Upgrade | Eagle Ford | Williams PLC Energy | Grimes LLC Services | Over Budget | 11880637.76 | 11922692.35 | 6012693.21 | 2354379.21 | 2082002.03 | 1473617.9 | 2025-01-23 | 2025-11-06 | 2025-09-29 | -38 | 3 | 211638.01 | 42054.59 | 0.35 | 1.78 | Yes | Clean | On Track | Low CO Impact
OG-1019 | Eagle Ford Facility Upgrade 20 | Facility Upgrade | Eagle Ford | Moreno, Walker and Robinson Energy | Garcia, Wright and Graham Services | Completed | 14993310.69 | 16674251.5 | 4820682.61 | 3306613.15 | 8052068.38 | 494887.36 | 2024-07-12 | 2025-02-14 | 2025-01-19 | -26 | 1 | 195835.08 | 1680940.81 | 11.21 | 1.31 | Yes | Medium Risk | Watch | Moderate CO Impact
OG-1020 | Gulf Coast Facility Upgrade 21 | Facility Upgrade | Gulf Coast | Williams PLC Energy | Ellis-Wheeler Services | Completed | 9582795.15 | 11251316.39 | 2543022.02 | 1707503.74 | 3480371.73 | 3520418.9 | 2025-02-18 | 2026-02-14 | 2026-02-18 | 4 | 4 | 167318.95 | 1668521.24 | 17.41 | 1.75 | No | High Risk | Critical | High CO Impact
OG-1021 | Eagle Ford Maintenance Turnaround 22 | Maintenance Turnaround | Eagle Ford | Weaver, Hill and Bowers Energy | Garcia, Wright and Graham Services | Over Budget | 7181923.26 | 7862523.98 | 757570.42 | 3213035.75 | 1348207.83 | 2543709.97 | 2025-11-06 | 2026-03-11 | 2026-03-20 | 9 | 2 | 291439.16 | 680600.72 | 9.48 | 4.06 | No | High Risk | Watch | Moderate CO Impact
OG-1022 | Gulf Coast Pipeline Construction 23 | Pipeline Construction | Gulf Coast | Weaver, Hill and Bowers Energy | Acosta, Graham and Odonnell Services | Over Budget | 3510366.91 | 3704741.8 | 2384250.89 | 157084.54 | 467444.16 | 695962.22 | 2025-08-22 | 2026-06-15 | 2026-07-26 | 41 | 6 | 87038.57 | 194374.89 | 5.54 | 2.48 | No | High Risk | Watch | Moderate CO Impact
OG-1023 | Eagle Ford Maintenance Turnaround 24 | Maintenance Turnaround | Eagle Ford | Smith LLC Energy | Cannon LLC Services | Delayed | 8209121.64 | 8856064.64 | 309165.81 | 1850781.18 | 2973106.59 | 3723011.06 | 2023-06-01 | 2024-03-22 | 2024-02-25 | -26 | 8 | 22774.86 | 646943 | 7.88 | 0.28 | Yes | Medium Risk | Watch | Moderate CO Impact
OG-1024 | Gulf Coast Well Drilling 25 | Well Drilling | Gulf Coast | Moreno, Walker and Robinson Energy | Garcia, Wright and Graham Services | Delayed | 8759460.23 | 10719628.61 | 1930250.04 | 1222406.1 | 7294225.19 | 272747.28 | 2025-11-01 | 2026-09-29 | 2026-10-25 | 26 | 4 | 499426.57 | 1960168.38 | 22.38 | 5.7 | No | High Risk | Critical | High CO Impact
OG-1025 | Eagle Ford Facility Upgrade 26 | Facility Upgrade | Eagle Ford | Hale, Garrett and Lee Energy | Ramirez PLC Services | Delayed | 9028072.28 | 7415676.63 | 102650.92 | 1939428.47 | 3749358.62 | 1624238.62 | 2025-07-25 | 2025-10-17 | 2025-11-14 | 28 | 6 | 44049.07 | -1612395.65 | -17.86 | 0.49 | No | Medium Risk | Under Budget | No Change Orders
OG-1026 | Gulf Coast Pipeline Construction 27 | Pipeline Construction | Gulf Coast | Hale, Garrett and Lee Energy | Daniel-Duarte Services | Active | 12648590.57 | 15411586.85 | 2625734.07 | 1887800.37 | 6039051.2 | 4859001.21 | 2023-06-09 | 2023-09-06 | 2023-09-22 | 16 | 6 | 392056.01 | 2762996.28 | 21.84 | 3.1 | No | High Risk | Critical | High CO Impact
OG-1027 | Eagle Ford Maintenance Turnaround 28 | Maintenance Turnaround | Eagle Ford | Weaver, Hill and Bowers Energy | Bautista-Caldwell Services | Active | 4494618.26 | 4973586.78 | 2729730.96 | 545897.31 | 188907.11 | 1509051.39 | 2025-01-07 | 2025-09-10 | 2025-10-19 | 39 | 1 | 56601.95 | 478968.52 | 10.66 | 1.26 | No | High Risk | Watch | Moderate CO Impact
OG-1028 | Gulf Coast Pipeline Construction 29 | Pipeline Construction | Gulf Coast | Williams PLC Energy | Bautista-Caldwell Services | Active | 1681213.6 | 1878310.89 | 168871.34 | 64676.48 | 822122.5 | 822640.57 | 2025-10-13 | 2026-02-08 | 2026-02-23 | 15 | 2 | 62420.56 | 197097.29 | 11.72 | 3.71 | No | High Risk | Watch | Moderate CO Impact
OG-1029 | Permian Basin Well Drilling 30 | Well Drilling | Permian Basin | Williams PLC Energy | Nelson, Miller and Johnson Services | Active | 9875876.9 | 8603600.14 | 2356311.47 | 4745287.98 | 682466.16 | 819534.53 | 2026-02-09 | 2026-07-04 | 2026-06-29 | -5 | 5 | 967570.46 | -1272276.76 | -12.88 | 9.8 | Yes | Clean | Under Budget | No Change Orders
OG-1030 | Gulf Coast Pipeline Construction 31 | Pipeline Construction | Gulf Coast | Moreno, Walker and Robinson Energy | Rodriguez, King and Wolfe Services | Completed | 13449725.56 | 11771812.98 | 6002256.62 | 501720.66 | 1215818.42 | 4052017.28 | 2025-08-07 | 2026-05-17 | 2026-04-06 | -41 | 3 | 279134.41 | -1677912.58 | -12.48 | 2.08 | Yes | Clean | Under Budget | No Change Orders
OG-1031 | Permian Basin Maintenance Turnaround 32 | Maintenance Turnaround | Permian Basin | Freeman, Barnes and Gonzalez Energy | Jacobs, Hood and Taylor Services | Completed | 5964134.77 | 6465469.82 | 31168.89 | 5803987.3 | 267259.23 | 363054.41 | 2024-03-16 | 2024-07-03 | 2024-07-12 | 9 | 3 | 228160.97 | 501335.05 | 8.41 | 3.83 | No | High Risk | Watch | Moderate CO Impact
OG-1032 | Midland Pipeline Construction 33 | Pipeline Construction | Midland | Munoz PLC Energy | Williams, Beard and Madden Services | Completed | 4168531.67 | 4892306.07 | 753637.17 | 823103.57 | 2378872.86 | 936692.46 | 2024-11-06 | 2025-11-02 | 2025-10-30 | -3 | 0 | 0 | 723774.4 | 17.36 | 0 | Yes | Medium Risk | Critical | High CO Impact
OG-1033 | Eagle Ford Pipeline Construction 34 | Pipeline Construction | Eagle Ford | Moreno, Walker and Robinson Energy | Garcia, Wright and Graham Services | Over Budget | 13273861.84 | 11904242.75 | 1668160.19 | 1472702.75 | 3118110.14 | 5645269.67 | 2023-12-14 | 2024-11-22 | 2024-12-11 | 19 | 4 | 346570.02 | -1369619.09 | -10.32 | 2.61 | No | Medium Risk | Under Budget | No Change Orders
OG-1034 | Permian Basin Well Drilling 35 | Well Drilling | Permian Basin | Munoz PLC Energy | Ellis-Wheeler Services | Completed | 2877340.91 | 3134363.51 | 1134848.91 | 868124.33 | 1112912.11 | 18478.15 | 2024-08-07 | 2025-03-17 | 2025-03-08 | -9 | 5 | 214934.4 | 257022.6 | 8.93 | 7.47 | Yes | Medium Risk | Watch | Moderate CO Impact
OG-1035 | Eagle Ford Facility Upgrade 36 | Facility Upgrade | Eagle Ford | Williams PLC Energy | Ramirez PLC Services | Over Budget | 2685834.72 | 2797945.5 | 275236.6 | 505219.37 | 1943444.98 | 74044.55 | 2025-06-09 | 2025-08-17 | 2025-08-02 | -15 | 4 | 178622.56 | 112110.78 | 4.17 | 6.65 | Yes | Clean | On Track | Low CO Impact
OG-1036 | Eagle Ford Pipeline Construction 37 | Pipeline Construction | Eagle Ford | Williams PLC Energy | Jacobs, Hood and Taylor Services | Delayed | 6391057.56 | 7839032.27 | 1368411.16 | 1326880.73 | 5038957.67 | 104782.72 | 2025-08-05 | 2025-10-31 | 2025-09-27 | -34 | 3 | 104296.64 | 1447974.71 | 22.66 | 1.63 | Yes | Medium Risk | Critical | High CO Impact
OG-1037 | Midland Well Drilling 38 | Well Drilling | Midland | Moreno, Walker and Robinson Energy | Williams, Beard and Madden Services | Active | 8700643.41 | 7076630.99 | 4367867.68 | 89746.1 | 493557.25 | 2125459.95 | 2026-03-05 | 2026-05-18 | 2026-05-08 | -10 | 3 | 77379 | -1624012.42 | -18.67 | 0.89 | Yes | Clean | Under Budget | No Change Orders
OG-1038 | Gulf Coast Well Drilling 39 | Well Drilling | Gulf Coast | Hale, Garrett and Lee Energy | Ramirez PLC Services | Completed | 8906435.71 | 6785828.87 | 1711434.74 | 275493.31 | 2814625.09 | 1984275.73 | 2023-10-05 | 2024-07-11 | 2024-06-29 | -12 | 2 | 1290.4 | -2120606.84 | -23.81 | 0.01 | Yes | Clean | Under Budget | No Change Orders
OG-1039 | Midland Maintenance Turnaround 40 | Maintenance Turnaround | Midland | Smith LLC Energy | Nelson, Miller and Johnson Services | Over Budget | 2901725.13 | 3408380.23 | 1329296.9 | 376930.62 | 327038.83 | 1375113.88 | 2023-03-19 | 2023-09-14 | 2023-10-18 | 34 | 5 | 141894.14 | 506655.1 | 17.46 | 4.89 | No | High Risk | Critical | High CO Impact
OG-1040 | Gulf Coast Well Drilling 41 | Well Drilling | Gulf Coast | Williams PLC Energy | Garcia, Wright and Graham Services | Completed | 2818241.62 | 3306746.5 | 623202.96 | 457349.12 | 2017907.62 | 208286.8 | 2025-03-26 | 2026-03-14 | 2026-02-25 | -17 | 7 | 92502.51 | 488504.88 | 17.33 | 3.28 | Yes | Medium Risk | Critical | High CO Impact
OG-1041 | Eagle Ford Pipeline Construction 42 | Pipeline Construction | Eagle Ford | Hale, Garrett and Lee Energy | Jacobs, Hood and Taylor Services | Delayed | 7393555.27 | 5920135.01 | 1732681.95 | 2452170.56 | 368315.78 | 1366966.73 | 2024-03-25 | 2024-09-28 | 2024-09-22 | -6 | 2 | 279776.21 | -1473420.26 | -19.93 | 3.78 | Yes | Clean | Under Budget | No Change Orders
OG-1042 | Eagle Ford Well Drilling 43 | Well Drilling | Eagle Ford | Freeman, Barnes and Gonzalez Energy | Shaw, Cabrera and Perry Services | Completed | 8105107.82 | 10088360.81 | 6381537.24 | 207744.73 | 896318.31 | 2602760.53 | 2026-01-13 | 2026-10-15 | 2026-10-25 | 10 | 6 | 573763.38 | 1983252.99 | 24.47 | 7.08 | No | High Risk | Critical | High CO Impact
OG-1043 | Gulf Coast Facility Upgrade 44 | Facility Upgrade | Gulf Coast | Silva PLC Energy | Jones Ltd Services | Completed | 5345741.49 | 5895004.17 | 2490775.66 | 562129.98 | 1538582.15 | 1303516.38 | 2024-03-03 | 2024-08-06 | 2024-06-28 | -39 | 1 | 95436.94 | 549262.68 | 10.27 | 1.79 | Yes | Medium Risk | Watch | Moderate CO Impact
OG-1044 | Permian Basin Maintenance Turnaround 45 | Maintenance Turnaround | Permian Basin | Munoz PLC Energy | Mendoza-Wagner Services | Delayed | 3249539.73 | 3517217.06 | 265249.38 | 1322966.7 | 592506.62 | 1336494.35 | 2023-04-30 | 2023-07-24 | 2023-09-02 | 40 | 4 | 54139.17 | 267677.33 | 8.24 | 1.67 | No | High Risk | Watch | Moderate CO Impact
OG-1045 | Eagle Ford Facility Upgrade 46 | Facility Upgrade | Eagle Ford | Munoz PLC Energy | Ramirez PLC Services | Delayed | 2154104.88 | 2542588.97 | 235382.8 | 2084067.19 | 87879.39 | 135259.59 | 2023-05-29 | 2024-01-20 | 2024-01-16 | -4 | 6 | 41379.25 | 388484.09 | 18.03 | 1.92 | Yes | Medium Risk | Critical | High CO Impact
OG-1046 | Eagle Ford Facility Upgrade 47 | Facility Upgrade | Eagle Ford | Williams and Sons Energy | Ellis-Wheeler Services | Completed | 1308449.5 | 1017166.6 | 124335.2 | 198256.89 | 354341.92 | 340232.59 | 2025-10-06 | 2025-12-18 | 2026-01-31 | 44 | 5 | 34091.63 | -291282.9 | -22.26 | 2.61 | No | Medium Risk | Under Budget | No Change Orders
OG-1047 | Gulf Coast Well Drilling 48 | Well Drilling | Gulf Coast | Munoz PLC Energy | Mendoza-Wagner Services | Completed | 13402808.05 | 13597034.94 | 4966133.11 | 3580931.92 | 4082202.3 | 967767.62 | 2025-03-17 | 2025-09-18 | 2025-09-23 | 5 | 8 | 370173.14 | 194226.89 | 1.45 | 2.76 | No | Medium Risk | On Track | Low CO Impact
OG-1048 | Eagle Ford Well Drilling 49 | Well Drilling | Eagle Ford | Freeman, Barnes and Gonzalez Energy | Daniel-Duarte Services | Over Budget | 3720727.75 | 4294279.52 | 911834.34 | 2235082.47 | 811622.69 | 335740.02 | 2023-11-07 | 2024-05-16 | 2024-04-12 | -34 | 1 | 53997.92 | 573551.77 | 15.42 | 1.45 | Yes | Medium Risk | Critical | High CO Impact
OG-1049 | Permian Basin Maintenance Turnaround 50 | Maintenance Turnaround | Permian Basin | Munoz PLC Energy | Harris, Lynn and Aguilar Services | Delayed | 7708954.04 | 6775095.52 | 1916824.16 | 1228758.53 | 2687292.34 | 942220.49 | 2025-05-08 | 2026-04-18 | 2026-05-12 | 24 | 6 | 798925.41 | -933858.52 | -12.11 | 10.36 | No | Medium Risk | Under Budget | No Change Orders

## Pivots
Row Labels | Average of Cost_Variance_Pct
Facility Upgrade | 1.1609
Maintenance Turnaround | 5.0182
Pipeline Construction | 2.674
Well Drilling | 0.35769
Grand Total | 2.2546
Row Labels | Average of Schedule_Variance_Days
Eagle Ford | 2.1053
Gulf Coast | -0.15385
Midland | -11.7
Permian Basin | 8.25
Grand Total | -0.26

## Dashboard
Oil and Gas Capital Project Portfolio
Filter by Region: | All
Total Budget |  | Total Actual Cost |  | Cost Variance |  | On-Time Rate
375070028.03 |  | 379205869.82 |  | 4135841.79 |  | 50%
Projects in Region |  | Region Budget |  | Region Actual Cost |  | Region On-Time Rate
50 |  | 375070028.03 |  | 379205869.82 |  | 50%
Top 5 Over-Budget Projects
Project ID | Project Name | Project Type | Region | Budgeted Cost | Actual Cost | Cost Variance | Cost Variance %
OG-1009 | Midland Pipeline Construction 10 | Pipeline Construction | Midland | 13899941.42 | 16952211.65 | 3052270.23 | 21.96
OG-1026 | Gulf Coast Pipeline Construction 27 | Pipeline Construction | Gulf Coast | 12648590.57 | 15411586.85 | 2762996.28 | 21.84
OG-1042 | Eagle Ford Well Drilling 43 | Well Drilling | Eagle Ford | 8105107.82 | 10088360.81 | 1983252.99 | 24.47
OG-1024 | Gulf Coast Well Drilling 25 | Well Drilling | Gulf Coast | 8759460.23 | 10719628.61 | 1960168.38 | 22.38
OG-1019 | Eagle Ford Facility Upgrade 20 | Facility Upgrade | Eagle Ford | 14993310.69 | 16674251.5 | 1680940.81 | 11.21